## 00_Project_Info
| Details | Comments
Project Name | AI Test Automation Project
Participants | Neha Tiwari, Priya A, Tejal Jayakar
Website URL | Retail Website <> | https://quality-fashion.lovable.app/
Workflow 1 | WF01_AI_TestCaseGeneration | Tejal's n8n workflow
Workflow 2 | WF02_AI_TestExecution | Priya's n8n workflow - QualityGrid Test Runner v4.0A/B
Workflow 3 | WF03_AI_BugTriage | Neha's n8n workflow
Shared Jira | Common Jira Project | https://automatedtcgen1.atlassian.net/jira/software/projects/RTA/boards/35/backlog
Shared Spreadsheet | AI_Test_Automation_Project
format (of XL) | Google sheet
Execution Tech Stack | Playwright + Playwright Express Server (local) + Cloudflared tunnel + n8n orchestrator
Result Validation | LLM-based comparison of Actual vs Expected Result, with confidence-based Pass/Fail/Needs Review routing

## 01_User_Stories
Story ID | Epic | Story Summary | Description | Acceptance Criteria | Priority | Status

## 02_Generated_Test_Cases
Test Case ID | Story ID | Unique Test Case Key | Epic | Feature | User Story Summary | Status | Version | Test Scenario | Test Objective | Preconditions | Test Steps | Test Data | Expected Result | Test Type | Priority | Generated By | AI Model | Prompt Version | Generation Date | Comments
TC001 | RTA-3 | RTA-3_TC001 | User Authentication | User Authentication | User Login | Draft | 1 | Verify Login Page UI Elements | Ensure all mandatory UI elements are present and visible on the login page. | User is on the application home page. | 1. Navigate to https://quality-fashion.lovable.app/. 2. Click the Login option. 3. Verify visibility of Username field, Password field, 'Forgot Password?' link, and 'Login' button. | N/A | Login page loads successfully. Username field, Password field, 'Forgot Password?' link, and 'Login' button are visible and correctly aligned. | UI | High | AI | Claude | v2 | 2026-07-17
TC002 | RTA-3 | RTA-3_TC002 | User Authentication | User Authentication | User Login | Draft | 1 | Successful Login with Valid Credentials (validuser) | Verify a registered customer can log in successfully and reach the dashboard. | Registered account exists (Username: validuser, Password: ValidPassword123!). User is on the login page. | 1. Enter 'validuser' in Username field. 2. Enter 'ValidPassword123!' in Password field. 3. Click Login button. | Username: validuser, Password: ValidPassword123! | Login succeeds. User is redirected to the account dashboard and greeted as 'validuser'. | Positive | High | AI | Claude | v2 | 2026-07-17
TC003 | RTA-3 | RTA-3_TC003 | User Authentication | User Authentication | User Login | Draft | 1 | Successful Login with Valid Credentials (demo.user1) | Verify a registered demo customer can log in successfully and reach the dashboard. | Registered account exists (Username: demo.user1, Password: Demo@123). User is on the login page. | 1. Enter 'demo.user1' in Username field. 2. Enter 'Demo@123' in Password field. 3. Click Login button. | Username: demo.user1, Password: Demo@123 | Login succeeds. User is redirected to the account dashboard and greeted as 'demo.user1'. | Positive | High | AI | Claude | v2 | 2026-07-17
TC004 | RTA-3 | RTA-3_TC004 | User Authentication | User Authentication | User Login | Draft | 1 | Login Failure with Invalid Username | Verify login fails with a proper error message when an unregistered username is used. | User is on the login page. | 1. Enter 'unregistereduser' in Username field. 2. Enter 'ValidPassword123!' in Password field. 3. Click Login button. | Username: unregistereduser, Password: ValidPassword123! | Login fails. Error message 'Invalid username or password' is displayed. User remains on the login page. | Negative | High | AI | Claude | v2 | 2026-07-17
TC005 | RTA-3 | RTA-3_TC005 | User Authentication | User Authentication | User Login | Draft | 1 | Login Failure with Invalid Password | Verify login fails with a proper error message when an incorrect password is used. | Registered account exists (Username: validuser). User is on the login page. | 1. Enter 'validuser' in Username field. 2. Enter 'WrongPassword!' in Password field. 3. Click Login button. | Username: validuser, Password: WrongPassword! | Login fails. Error message 'Invalid username or password' is displayed. User remains on the login page. | Negative | High | AI | Claude | v2 | 2026-07-17
TC006 | RTA-3 | RTA-3_TC006 | User Authentication | User Authentication | User Login | Draft | 1 | Login Attempt with Empty Credentials | Verify the system validates empty username and password fields. | User is on the login page. | 1. Leave Username field empty. 2. Leave Password field empty. 3. Click Login button. | Username:, Password: | Validation messages indicate both Username and Password fields are required. Login is blocked. | Validation | Medium | AI | Claude | v2 | 2026-07-17
TC007 | RTA-3 | RTA-3_TC007 | User Authentication | User Authentication | User Login | Draft | 1 | Login Attempt with Empty Username | Verify validation when Username is empty but Password is provided. | User is on the login page. | 1. Leave Username field empty. 2. Enter 'ValidPassword123!' in Password field. 3. Click Login button. | Username: '', Password: ValidPassword123! | Validation message indicates Username is required. Login is blocked. | Validation | Medium | AI | Claude | v2 | 2026-07-17
TC008 | RTA-3 | RTA-3_TC008 | User Authentication | User Authentication | User Login | Draft | 1 | Login Attempt with Empty Password | Verify validation when Password is empty but Username is provided. | User is on the login page. | 1. Enter 'validuser' in Username field. 2. Leave Password field empty. 3. Click Login button. | Username: validuser, Password: '' | Validation message indicates Password is required. Login is blocked. | Validation | Medium | AI | Claude | v2 | 2026-07-17
TC009 | RTA-3 | RTA-3_TC009 | User Authentication | User Authentication | User Login | Draft | 1 | Username Field Maximum Character Limit | Verify the Username field enforces the maximum allowed character limit. | User is on the login page. | 1. Enter a username exceeding 10 characters in the Username field. 2. Enter a valid password. 3. Click Login button. | Username: asdgsgsgsgerwe, Password: ValidPassword123! | The field does not accept usernames longer than 10 characters and displays the error message 'Username should not exceed 10 characters.' | Boundary | Medium | AI | Claude | v2 | 2026-07-17
TC010 | RTA-3 | RTA-3_TC010 | User Authentication | User Authentication | User Login | Draft | 1 | Case Sensitivity of Password Field | Verify the Password field is case-sensitive during authentication. | Registered account exists (Username: demo.user2, Password: Demo@123). User is on the login page. | 1. Enter 'demo.user2' in Username field. 2. Enter 'demo@123' (incorrect casing) in Password field. 3. Click Login button. | Username: demo.user2, Password: demo@123 | Login fails with 'Invalid username or password' message, confirming the password field is case-sensitive. | Boundary | High | AI | Claude | v2 | 2026-07-17
TC011 | RTA-3 | RTA-3_TC011 | User Authentication | User Authentication | User Login | Draft | 1 | XSS Script Injection in Username Field | Verify the login form safely handles script injection attempts. | User is on the login page. | 1. Enter a script tag payload in the Username field. 2. Enter any password. 3. Click Login button. 4. Verify no popup/alert appears. | Username: <script>alert('XSS')</script>, Password: Test@123 | Input is safely rejected or sanitized as plain text. No script executes and no alert/popup appears. Login fails as invalid credentials. | Security | High | AI | Claude | v2 | 2026-07-17
TC012 | RTA-3 | RTA-3_TC012 | User Authentication | User Authentication | User Login | Draft | 1 | SQL-style Injection String as Username | Verify the login form safely rejects SQL-injection-style input without granting unauthorized access. | User is on the login page. | 1. Enter a SQL-injection-style payload in the Username field. 2. Enter the same payload in the Password field. 3. Click Login button. | Username: ' OR '1'='1, Password: ' OR '1'='1 | Login is safely rejected as invalid credentials. No unauthorized access is granted and the application does not error out or crash. | Security | High | AI | Claude | v2 | 2026-07-17
TC013 | RTA-3 | RTA-3_TC013 | User Authentication | User Authentication | User Login | Draft | 1 | Password Field Character Masking | Verify characters entered in the Password field are masked for security. | User is on the login page. | 1. Click the Password field. 2. Type any characters. 3. Observe the displayed characters. | Password: MySecretPassword | Characters are masked (shown as dots/asterisks). The plain text password is never visible on screen. | UI | High | AI | Claude | v2 | 2026-07-17
TC014 | RTA-3 | RTA-3_TC014 | User Authentication | User Authentication | User Login | Draft | 1 | Keyboard Navigation Through Login Form | Verify all interactive elements on the login page can be navigated using the keyboard. | User is on the login page. | 1. Press Tab repeatedly from page load. 2. Verify focus moves sequentially through Username, Password, Forgot Password link, and Login button. 3. Press Enter on the Login button with focus. | N/A | All elements are reachable using the Tab key in a logical order, a visible focus outline appears on each element in turn, and pressing Enter while the Login button is focused submits the form. | Accessibility | Medium | AI | Claude | v2 | 2026-07-17
TC015 | RTA-3 | RTA-3_TC015 | User Authentication | User Authentication | User Login | Draft | 1 | ARIA Labels on Login Fields | Verify input fields and the login button expose correct accessible names for screen readers. | User is on the login page. | 1. Inspect the Username field for an accessible label/ARIA attribute. 2. Inspect the Password field for an accessible label/ARIA attribute. 3. Inspect the Login button for an accessible name. | N/A | The Username field, Password field, and Login button each have a non-empty accessible name exposed via a <label>, aria-label, or aria-labelledby attribute. | Accessibility | Medium | AI | Claude | v2 | 2026-07-17
TC016 | RTA-3 | RTA-3_TC016 | User Authentication | User Authentication | User Login | Draft | 1 | Forgot Password Link Redirection | Verify clicking the 'Forgot Password?' link redirects the user to the correct recovery page. | User is on the login page. | 1. Click the 'Forgot Password?' link. 2. Observe the resulting page/URL. | N/A | User is successfully redirected to a password reset/recovery page at a distinct URL from the login page. | Positive | High | AI | Claude | v2 | 2026-07-17 | Intentional bug for QA demo - link does not navigate correctly. Expected to FAIL.
TC017 | RTA-3 | RTA-3_TC017 | User Authentication | User Authentication | User Login | Draft | 1 | Forgot Password Recovery Page Contains Email Field | Verify the password recovery page displays the elements needed to request a reset. | User is on the login page. | 1. Click the 'Forgot Password?' link. 2. Verify the resulting page displays an email input field and a Submit/Reset button. | N/A | The recovery page loads with a visible email input field and a submit button for password reset. | UI | Medium | AI | Claude | v2 | 2026-07-17 | Dependent on TC016 - expected to FAIL due to the same Forgot Password redirect bug.
TC018 | RTA-3 | RTA-3_TC018 | User Authentication | User Authentication | User Login | Draft | 1 | Login with demo.user3 Redirects to Dashboard | Verify demo.user3 can log in successfully and reach the account dashboard. | Registered account exists (Username: demo.user3, Password: Demo@123). User is on the login page. | 1. Enter 'demo.user3' in Username field. 2. Enter 'Demo@123' in Password field. 3. Click Login button. | Username: demo.user3, Password: Demo@123 | Login succeeds and the user is redirected to the account dashboard URL. | Positive | High | AI | Claude | v2 | 2026-07-17 | Intentional bug for QA demo - demo.user3 authenticates but is not navigated to the dashboard. Expected to FAIL.
TC019 | RTA-3 | RTA-3_TC019 | User Authentication | User Authentication | User Login | Draft | 1 | demo.user3 Dashboard Widgets Visible Post-Login | Verify the dashboard summary widgets render correctly for demo.user3 after login. | Registered account exists (Username: demo.user3, Password: Demo@123). User is on the login page. | 1. Log in as demo.user3. 2. Verify the dashboard displays Total Orders, Wishlist, Cart Items, and Total Spent widgets. | Username: demo.user3, Password: Demo@123 | The dashboard loads with all four summary widgets (Total Orders, Wishlist, Cart Items, Total Spent) visible for demo.user3. | Positive | Medium | AI | Claude | v2 | 2026-07-17 | Dependent on TC018 - dashboard never loads for demo.user3, so widgets cannot be verified. Expected to FAIL.
TC020 | RTA-3 | RTA-3_TC020 | User Authentication | User Authentication | User Login | Draft | 1 | Login with Leading/Trailing Whitespace in Username | Verify login behavior when the username contains leading/trailing whitespace. | Registered account exists (Username: demo.user4, Password: Demo@123). User is on the login page. | 1. Enter ' demo.user4 ' (with leading/trailing spaces) in Username field. 2. Enter 'Demo@123' in Password field. 3. Click Login button. | Username: demo.user4 , Password: Demo@123 | The system trims whitespace and logs the user in successfully, OR displays a clear validation message if whitespace is not permitted. | Edge | Low | AI | Claude | v2 | 2026-07-17
TC001 | RTA-2 | RTA-2_TC001 | User Authentication | User Registration | User Registration | Draft | 1 | Verify Registration page navigation | Ensure the Registration page loads successfully when the Sign Up button is clicked from the home page. | User is on the RetailHub home page. User is not logged in. | 1. Locate the Sign Up button in the top right corner of the home page. 2. Click on the Sign Up button. 3. Verify the URL and the loaded page content. | N/A | The Registration page loads successfully with all form fields visible. | UI | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC002 | RTA-2 | RTA-2_TC002 | User Authentication | User Registration | User Registration | Draft | 1 | Successful registration with all valid fields | Verify that a new user can register successfully by filling in all mandatory and optional fields with valid data. | User is on the Registration page. | 1. Enter valid First Name (e.g., John). 2. Enter valid Last Name (e.g., Doe). 3. Enter unique and valid Email Address. 4. Enter valid Phone number. 5. Enter unique Username. 6. Enter valid Password. 7. Enter matching Confirm Password. 8. Click the Sign Up/Submit button. | First Name: John, Last Name: Doe, Email: john.doe@example.com, Phone: 1234567890, Username: johndoe123, Password: Password123!, Confirm Password: Password123! | Registration succeeds and a success confirmation is displayed to the user. | Positive | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC003 | RTA-2 | RTA-2_TC003 | User Authentication | User Registration | User Registration | Draft | 1 | Registration with missing mandatory fields | Verify that registration fails and appropriate error messages are displayed when mandatory fields are left empty. | User is on the Registration page. | 1. Leave First Name, Last Name, Email, Password, and Confirm Password fields blank. 2. Enter details in optional fields (e.g., Phone). 3. Click the Sign Up/Register button. | First Name: '', Last Name: '', Email: '', Phone: 1234567890, Password: '', Confirm Password: '' | Registration fails. Validation errors are displayed for each missing mandatory field stating they are required. | Validation | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC004 | RTA-2 | RTA-2_TC004 | User Authentication | User Registration | User Registration | Draft | 1 | Registration with an already registered email address | Verify that registration fails when attempting to register with an email address that is already associated with an existing account. | An account with email 'existing.user@example.com' already exists. User is on the Registration page. | 1. Enter valid First Name and Last Name. 2. Enter 'existing.user@example.com' in the Email Address field. 3. Enter valid Phone, Username, Password, and Confirm Password. 4. Click the Sign Up button. | Email: existing.user@example.com | Registration fails. An error message 'Email address is already registered' is displayed. | Negative | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC005a | RTA-2 | RTA-2_TC005a | User Authentication | User Registration | User Registration | Draft | 1 | Boundary - First Name minimum length (1 character) | Verify system behavior when First Name is below the minimum length. | User is on the Registration page. | 1. Enter 'A' in the First Name field. 2. Fill all other fields validly. 3. Click the Sign Up button. | First Name: A | Registration is blocked and a validation message indicates First Name must be at least 2 characters. | Boundary | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC005b | RTA-2 | RTA-2_TC005b | User Authentication | User Registration | User Registration | Draft | 1 | Boundary - First Name maximum valid length (50 characters) | Verify system behavior when First Name is exactly at the maximum allowed length. | User is on the Registration page. | 1. Enter a 50-character First Name. 2. Fill all other fields validly. 3. Click the Sign Up button. | First Name: AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA | Registration succeeds with the 50-character First Name accepted. | Boundary | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC005c | RTA-2 | RTA-2_TC005c | User Authentication | User Registration | User Registration | Draft | 1 | Boundary - First Name exceeding maximum length (51 characters) | Verify system behavior when First Name exceeds the maximum allowed length. | User is on the Registration page. | 1. Enter a 51-character First Name. 2. Fill all other fields validly. 3. Click the Sign Up button. | First Name: AAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAAA | Registration is blocked and a field length validation error is displayed for First Name exceeding 50 characters. | Boundary | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC006 | RTA-2 | RTA-2_TC006 | User Authentication | User Registration | User Registration | Draft | 1 | Invalid Email Address format validation | Verify that registration is prevented and validation error displays when email is in an incorrect format. | User is on the Registration page. | 1. Enter the invalid email format 'plainaddress'. 2. Complete other fields with valid data. 3. Click the Sign Up button. | Email: plainaddress | Registration fails. A field-level validation message 'Please enter a valid email address' is displayed. | Validation | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC007 | RTA-2 | RTA-2_TC007 | User Authentication | User Registration | User Registration | Draft | 1 | Password and Confirm Password mismatch validation | Verify that registration fails if the Confirm Password field does not match the Password field. | User is on the Registration page. | 1. Fill in all fields with valid information. 2. Enter 'SecurePass123' in the Password field. 3. Enter 'DifferentPass123' in the Confirm Password field. 4. Click the Sign Up button. | Password: SecurePass123, Confirm Password: DifferentPass123 | Registration fails. An error message 'Passwords do not match' is displayed near the Confirm Password field. | Validation | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC008a | RTA-2 | RTA-2_TC008a | User Authentication | User Registration | User Registration | Draft | 1 | Boundary - Password minimum length (7 characters, invalid) | Verify password field rejects a password below the minimum length. | User is on the Registration page. | 1. Enter a 7-character password in both Password and Confirm Password fields. 2. Click Sign Up. | Password: P@ss12, Confirm Password: P@ss12 | Registration is blocked and error message 'Password must be at least 8 characters' is displayed. | Boundary | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC008b | RTA-2 | RTA-2_TC008b | User Authentication | User Registration | User Registration | Draft | 1 | Boundary - Password maximum valid length (20 characters) | Verify password field accepts a password at the maximum allowed length. | User is on the Registration page. | 1. Enter a 20-character password in both Password and Confirm Password fields. 2. Click Sign Up. | Password: P@ssword123456789012, Confirm Password: P@ssword123456789012 | Registration succeeds with the 20-character password accepted. | Boundary | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC008c | RTA-2 | RTA-2_TC008c | User Authentication | User Registration | User Registration | Draft | 1 | Boundary - Password exceeding maximum length (21 characters) | Verify password field rejects a password exceeding the maximum length. | User is on the Registration page. | 1. Enter a 21-character password in both Password and Confirm Password fields. 2. Click Sign Up. | Password: P@ssword1234567890123, Confirm Password: P@ssword1234567890123 | Registration is blocked and a password length validation error is displayed for exceeding 20 characters. | Boundary | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC009 | RTA-2 | RTA-2_TC009 | User Authentication | User Registration | User Registration | Draft | 1 | Security - Password complexity rules and masking | Ensure passwords require complex criteria and are masked when typed in the input fields. | User is on the Registration page. | 1. Verify Password and Confirm Password field inputs are masked. 2. Attempt registration with a simple password 'password' that lacks complexity. 3. Attempt registration with a complex password. | Simple: password, Complex: SecureP@ss1 | Password characters are masked. The simple password registration fails with a password policy error, and the complex password registration succeeds. | Security | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC010 | RTA-2 | RTA-2_TC010 | User Authentication | User Registration | User Registration | Draft | 1 | UI verification of mandatory field indicators | Verify that all mandatory fields are clearly identified on the UI. | User is on the Registration page. | 1. Load the registration page. 2. Visually inspect the fields: First Name, Last Name, Email, Password, Confirm Password, Username, Phone. | N/A | All mandatory fields have a clear red asterisk (*) or visual indicator next to their label. | UI | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC011 | RTA-2 | RTA-2_TC011 | User Authentication | User Registration | User Registration | Draft | 1 | Accessibility - Keyboard Navigation (Tab Order) | Ensure a user can navigate through all interactive elements of the registration form using only the keyboard. | User is on the Registration page. Mouse is not used. | 1. Set focus on the First Name field. 2. Press Tab repeatedly to move through all fields and the submit button. | N/A | Keyboard focus moves in a logical top-to-bottom order through all fields and the Sign Up button. | Accessibility | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC012 | RTA-2 | RTA-2_TC012 | User Authentication | User Registration | User Registration | Draft | 1 | Accessibility - Screen reader compatibility and ARIA Labels | Verify that form inputs have descriptive ARIA labels or associated labels for accessibility screen readers. | Registration page is loaded. | 1. Inspect each field for an accessible label. 2. Trigger a validation error and verify it is exposed via an ARIA live region or associated error text. | N/A | Each field exposes a non-empty accessible name, and validation error text is programmatically associated with its field. | Accessibility | Low | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC013 | RTA-2 | RTA-2_TC013 | User Authentication | User Registration | User Registration | Draft | 1 | Security - Input sanitization (XSS and SQL Injection mitigation) | Verify that the input fields handle injection payloads gracefully and do not execute raw scripts or database commands. | User is on the Registration page. | 1. Enter a script tag payload in the First Name field. 2. Fill in other fields normally and click Sign Up. | First Name: <script>alert(1)</script> | The system rejects or sanitizes the input. No script executes and no error page/crash occurs. | Security | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC014 | RTA-2 | RTA-2_TC014 | User Authentication | User Registration | User Registration | Draft | 1 | Validation - Invalid Phone Number format | Verify that entering alphabetical characters in the Phone field triggers validation. | User is on the Registration page. | 1. Fill out all mandatory fields validly. 2. Enter letters 'abcde' in the Phone field. 3. Click Sign Up. | Phone: abcde | Registration fails. A validation error such as 'Please enter a valid phone number' is displayed. | Validation | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC015 | RTA-2 | RTA-2_TC015 | User Authentication | User Registration | User Registration | Draft | 1 | Positive - Multi-click submission prevention | Verify that clicking the Sign Up button multiple times concurrently does not trigger duplicate registration requests. | User is on the Registration page with valid registration data filled. | 1. Fill out all fields with valid details. 2. Click the Sign Up button rapidly multiple times. | Valid registration data (see TC002) | The Sign Up button is disabled immediately after the first click, and only one registration request is sent. | Positive | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC016 | RTA-2 | RTA-2_TC016 | User Authentication | User Registration | User Registration | Draft | 1 | UI - Responsive design verification | Verify that the registration page adapts correctly to different screen viewport sizes. | User accesses the web app. | 1. Open the Registration page on a Desktop browser. 2. Resize to Tablet viewport (768px). 3. Resize to Mobile viewport (375px). | N/A | The layout adjusts dynamically at each viewport with no overlapping or clipped elements. | UI | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC001 | RTA-30 | RTA-30_TC001 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify Cart button presence and layout in header | Verify that the Cart icon/button is consistently displayed in the top-right section of the header on all standard website pages. | User is on the RetailHub website homepage. | 1. Open the website homepage. 2. Observe the header section. 3. Navigate to 'About Us', 'Product Listing', and 'Contact Us' pages, observing the header each time. | N/A | The Cart button/icon is visible in the top-right section of the header across all tested pages. | UI | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC002 | RTA-30 | RTA-30_TC002 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify navigation to Cart page from Home page | Confirm that clicking the Cart button on the homepage successfully redirects the user to the Cart page. | User is on the Homepage. | 1. Locate the Cart button in the top-right header. 2. Click on the Cart button. | N/A | User is successfully redirected to the Cart page and the Cart page contents are loaded. | Positive | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC003 | RTA-30 | RTA-30_TC003 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify empty cart display message | Verify that the Cart page shows 'Your cart is empty' when no products have been added. | The shopping cart is empty. | 1. Click on the Cart button from the header to open the Cart page. | N/A | The Cart page displays the text 'Your cart is empty' and no product grid or subtotal calculations are visible. | Positive | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC004 | RTA-30 | RTA-30_TC004 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify cart item list and product details | Confirm that the Cart page lists added items along with their details, quantity, and price. | At least two different items are added to the cart. | 1. Navigate to the Product Listing page. 2. Add Product A and Product B to the cart. 3. Click the Cart button to navigate to the Cart page. 4. Inspect the item listings, unit prices, and quantities. | Product A Price: 10.00, Product A Quantity: 1, Product B Price: 15.50, Product B Quantity: 2 | The Cart page displays both products with matching name, unit price, quantity, and subtotal per item. | Positive | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC005 | RTA-30 | RTA-30_TC005 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify total cart value calculation | Verify that the Cart page displays the mathematically correct total cart value for all added items. | Multiple items with varying prices and quantities are added to the cart. | 1. Add 3 units of Product A ($20.00 each) and 1 unit of Product B ($50.00) to the cart. 2. Click the Cart button to open the Cart page. 3. Verify the calculated total cart value displayed. | Product A Price: 20.00, Product A Quantity: 3, Product B Price: 50.00, Product B Quantity: 1 | The total cart value displays accurately as $110.00. | Positive | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC006 | RTA-30 | RTA-30_TC006 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify cart navigation from About Us page | Confirm that clicking the Cart button on the 'About Us' page redirects the user to the Cart page. | User is on the About Us page. | 1. Click on the Cart button in the top-right header. | N/A | User is successfully redirected to the Cart page. | Positive | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC007 | RTA-30 | RTA-30_TC007 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify cart navigation from Product Listing page | Confirm that clicking the Cart button on the 'Product Listing' page redirects the user to the Cart page. | User is on the Product Listing page. | 1. Click on the Cart button in the top-right header. | N/A | User is successfully redirected to the Cart page. | Positive | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC008 | RTA-30 | RTA-30_TC008 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify cart navigation from Contact Us page | Confirm that clicking the Cart button on the 'Contact Us' page redirects the user to the Cart page. | User is on the Contact Us page. | 1. Click on the Cart button in the top-right header. | N/A | User is successfully redirected to the Cart page. | Positive | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC009a | RTA-30 | RTA-30_TC009a | Product Catalog | View Cart | View Cart | Draft | 1 | Boundary - Cart quantity at maximum allowed limit (99) | Verify system behavior when item quantity is set to the maximum allowed boundary. | Maximum allowed quantity per line item is 99. A product is in the cart. | 1. Add a product to the cart. 2. Navigate to the Cart page. 3. Change the quantity of the product to 99. | Quantity: 99 | The quantity of 99 is accepted and the subtotal recalculates correctly. | Boundary | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC009b | RTA-30 | RTA-30_TC009b | Product Catalog | View Cart | View Cart | Draft | 1 | Boundary - Cart quantity exceeding maximum allowed limit (100) | Verify system behavior when item quantity is set past the maximum allowed boundary. | Maximum allowed quantity per line item is 99. A product is in the cart. | 1. Add a product to the cart. 2. Navigate to the Cart page. 3. Attempt to change the quantity of the product to 100. | Quantity: 100 | The system blocks the input or displays a validation message indicating the maximum quantity limit of 99 has been reached. | Boundary | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC010 | RTA-30 | RTA-30_TC010 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify cart updates dynamically when quantity changes | Confirm that updating the quantity of a product inside the Cart page immediately recalculates subtotals and the total value dynamically. | One item priced at $15.00 is in the cart. | 1. Navigate to the Cart page. 2. Increase the item quantity from 1 to 3. 3. Observe totals. 4. Decrease the quantity from 3 to 2. 5. Observe totals. | Item Price: 15.00 | When quantity increases to 3, the total updates to $45.00 without a manual page refresh; when decreased to 2, it updates to $30.00. | Validation | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC011 | RTA-30 | RTA-30_TC011 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify cart behavior for deactivated products | Check cart behavior when a product in the cart is deactivated or goes out of stock in the backend. | Product A is added to the user's cart. | 1. Add Product A to cart. 2. Deactivate Product A (mark Out of Stock) via admin/mock data. 3. Navigate to or refresh the Cart page. | Product A Status: Deactivated | The cart displays an alert that Product A is no longer available, excludes its value from the total, and disables checkout. | Negative | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC012 | RTA-30 | RTA-30_TC012 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify Cart URL isolation per session | Verify that a user's cart cannot be accessed or manipulated by other users via URL parameter tampering. | Two distinct active browser sessions (User A and User B). | 1. In User A's session, add items to cart and navigate to the Cart page. 2. Copy the active Cart page URL. 3. Open the URL in User B's session. 4. Check if User A's cart items are visible to User B. | N/A | User B is restricted from viewing User A's cart and is instead shown their own isolated cart contents or an empty cart. | Security | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC013 | RTA-30 | RTA-30_TC013 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify keyboard navigation to Cart button | Verify that the Cart icon in the header can be focused and activated using only the keyboard. | User is navigating the website using a keyboard. | 1. Load the Homepage. 2. Press Tab repeatedly until the Cart button receives focus. 3. Press Enter to activate it. | N/A | The Cart button receives a visible focus outline, and pressing Enter successfully opens the Cart page. | Accessibility | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC014 | RTA-30 | RTA-30_TC014 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify screen reader accessibility for Cart button | Ensure that screen readers properly announce the Cart icon name and the current count of items in it. | Screen reader is active. | 1. Navigate to the Homepage with screen reader enabled. 2. Move focus to the Cart button. 3. Verify the spoken output. | N/A | The screen reader announces the element as a shopping cart along with the current item count. | Accessibility | Medium | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC015 | RTA-30 | RTA-30_TC015 | Product Catalog | View Cart | View Cart | Draft | 1 | Verify responsive layout of Cart icon and page | Ensure the Cart button and Cart page layout resize gracefully on smaller mobile viewports. | Browser developer tools are available. | 1. Open the Homepage and switch viewport to mobile view (375px). 2. Verify Cart button position. 3. Click Cart button and verify page layout on mobile viewport. | Mobile viewport: 375px width | The Cart button fits within the mobile header and the Cart page layout scales without clipped text or horizontal scrollbars. | UI | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15
TC016 | RTA-30 | RTA-30_TC016 | Product Catalog | View Cart | View Cart | Obsolete | 1 | Verify persistence of cart items on page reload | Confirm that items added to the cart remain saved when performing page reloads and back-and-forth navigation. | User has added items to the cart. | 1. Add 2 items to the cart. 2. Navigate to the Cart page and verify the items exist. 3. Refresh the browser page. 4. Navigate to 'About Us' then back to the Cart page. | N/A | The cart contents persist across page reloads and step navigation, displaying identical items, quantities, and totals. | Validation | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15 | Superseded by v2.0 of this test case after the underlying user story was updated in Jira.
TC016 | RTA-30 | RTA-30_TC016 | Product Catalog | View Cart | View Cart | Draft | 2 | Verify persistence of cart items on page reload | Confirm that items added to the cart remain saved when performing page reloads and back-and-forth navigation. | User has added items to the cart. | 1. Add 2 items to the cart. 2. Navigate to the Cart page and verify the items exist. 3. Refresh the browser page. 4. Navigate to 'About Us' then back to the Cart page. | N/A | The cart contents persist across page reloads and step navigation, displaying identical items, quantities, and totals. | Validation | High | WF01 - AI Test Case Generator | Gemini 3.5 Flash | v1.0 | 2026-07-15

## 03_Execution_Results
Unique Test Case Key | Version | Test Case ID | Story ID | Execution Date | Executed By | Browser | Environment | Actual Result | Expected Result | Execution Status | Confidence Score | Screenshot/Evidence | Execution Duration | Comments

## 04_Bug_Report
Bug ID | Unique Test Case Key | Test Case ID | Story ID | Epic | Bug Summary | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Assigned To | Created Date | Jira Bug ID | Jira URL | Comments

## 05_Lookups
Category | Value
Test Type | Positive
Test Type | Negative
Test Type | Boundary
Test Type | Edge
Test Type | Validation
Test Type | UI
Test Type | Security
Test Type | Accessibility
Priority | High
Priority | Medium
Priority | Low
Severity | Critical
Severity | High
Severity | Medium
Severity | Low
TC Status | Draft
TC Status | Obsolete
Execution Status | Pass
Execution Status | Fail
Execution Status | Needs Review
Execution Status | Blocked
Bug Status | Open
Bug Status | Assigned
Bug Status | In Progress
Bug Status | Resolved
Bug Status | Closed

## 06_Dashboard
Metric | Value
Total User Stories
Total Test Cases
Passed
Failed
Needs Review
Blocked
Open Bugs
Closed Bugs

## 07_Test_Data
User_ID | Username | Password | User_Type | Role | Status
U001 | demo.user1 | Demo@123 | Registered | Customer | Active
U002 | demo.user2 | Demo@123 | Registered | Customer | Active
U003 | demo.user3 | Demo@123 | Registered | Customer | Active
U004 | demo.user4 | Demo@123 | Registered | Customer | Active
U005 | demo.user5 | Demo@123 | Registered | Customer | Active
A001 | admin | admin123 | Admin | Admin | Active

## 08_Execution_Config
Parameter | Value
Application_Name | Quality Fashion
Base_URL | https://quality-fashion.lovable.app
Browser | Chrome
Execution_Mode | Automated - Playwright
Test_Runner | QualityGrid Test Runner v4.0A/v4.0B
Execution_Host | Playwright Express Server (local) via Cloudflared tunnel
Orchestrator | n8n
Result_Validation | LLM-based comparison (Actual vs Expected) with confidence routing
Guest_Checkout | Allowed
Login_Required_For_Checkout | Yes
Cart_Persistence | Enabled
Order_History | Enabled
Jira_Project | RTA
Jira_Board | https://automatedtcgen1.atlassian.net/jira/software/projects/RTA/boards/35